## Backend
ID | Task ID | Test Objective | Test Steps | Expected Result | Actual Result | Pass/Fail | Date | Done by:
1 | createUser | Sikeres user létrehozása |  | 201-es kód: User sikeresen létrehozva | 201-es kód: User sikeresen létrehozva | Pass | 2026-01-06 | Pásztor Kevin
2 | createUser | Foglalt email cím ellenőrzése |  | 409-es kód: Üzenetet küldd, hogy az email-cím foglalt | 409-es kód: Üzenetet küldd, hogy az email-cím foglalt | Pass | 2026-01-08 | Pásztor Kevin
3 | createUser | Túl rövid jelszó beírása |  | 400-as kód: Üzenetet küldd hogy a jelszónak legalább 6 karakternek kell lennie | 400-as kód: Üzenetet küldd hogy a jelszónak legalább 6 karakternek kell lennie | Pass | 2026-01-08 | Pásztor Kevin
4 | deleteUser | Meglévő felhasználó eltávolítása az adatbázisból |  | 200-as kód: Felhasználó sikeresen eltávolítva | 404-es kód: Not found | Fail | 2026-01-08 | Pásztor Kevin
5 | AddOrder | Sikeres rendelés leadása |  | 201-es kód: Rendelés sikeres leadása | 404-es kód: Not found | Fail | 2026-01-08 | Pásztor Kevin
6 | AddOrder | Sikeres rendelés leadása |  | 201-es kód: Rendelés sikeres leadása | 201-es kód: Rendelés sikeres leadása | Pass | 2026-01-09 | Pásztor Kevin
7 | DeleteOrder | Rendelés sikeres törlése |  | 200-as kód: Rendelés sikeres törlése | 200-as kód:Rendelés sikeres törlése | Pass | 2026-01-09 | Pásztor Kevin
8 | CPG-26 | Összes étel lekérdezése | GetAllDishes eljárás meghívása, és futtatása | 200-as kód: Összes rendelés sikeres lekérdezése | 200-as kód: Összes rendelés sikeres lekérdezése | Pass | 2026-01-20 | Pásztor Kevin
9 | CPG-26 | Egy étel lekérdezése az ID-ja alapján | GetDishByID eljárás meghívása, majd egy étel ID-t beírni (pl: dishes/GetDishById/99) | 200-as kód: Étel sikeres lekérezése ID alapján | 404-es kód: Not found | Fail | 2026-01-20 | Pásztor Kevin
10 | CPG-26 | Egy étel lekérdezése az ID-ja alapján | GetDishByID eljárás meghívása, majd egy étel ID-t beírni (pl: dishes/GetDishById/99) | 200-as kód: Étel sikeres lekérezése ID alapján | 200-as kód: étel sikeres lekérdezése ID alapján | Pass | 2026-01-20 | Pásztor Kevin
11 | CPG-26 | Egy étel hozzáadása az adatbázisba | AddDish eljárás meghívása, majd az adatok beírása | 201-as kód: Étel sikeres hozzáadása az adatbázishoz | 500-as kód: Adatbázis hiba | Fail | 2026-01-20 | Pásztor Kevin
12 | CPG-26 | Egy étel hozzáadása az adatbázisba | AddDish eljárás meghívása, majd az adatok beírása | 201-as kód: Étel sikeres hozzáadása az adatbázishoz | 201-as kód: Étel sikeres hozzáadása az adatbázishoz | Pass | 2026-01-20 | Pásztor Kevin
13 | CPG-26 | Egy étel törlése az adatbázisból | DeleteDish eljárás meghívása és az étel ID beírásával (pl: dishes/DeleteDish/5) | 200-as kód: Sikeresen törlődött | 200-as kód: Sikeresen törlődött | Pass | 2026-01-20 | Pásztor Kevin
14 | CPG-26 | Egy étel törlése az adatbázisból | DeleteDish eljárás meghívása és az étel ID beírásával (pl: dishes/DeleteDish/5) | 404-es kód: Az étel nem található | 404-es kód: Az étel nem található | Pass | 2026-01-20 | Pásztor Kevin
15 | CPG-26 | Restaurant ID alapján lekérdezi az összes ételt az étteremben | GetAllDishesByRestaurant eljárás meghívása és egy étterem ID-ját megadni. | 200-as kód: Minden étel az étteremben sikeres lekérdezése | 200-as kód: Minden étel az étteremben sikeres lekérdezése | Pass | 2026-01-20 | Pásztor Kevin
16 | CPG-26 | Egy étel adatainak módosítása ID alapján | UpdateDish eljárás meghívása és a módosítani kívánt étel ID-ját megadni. | 200-as kód: Étel sikeres frissítése | 415-ös kód: Unsopported media type | Fail | 2026-01-20 | Pásztor Kevin
17 | CPG-26 | Egy étel adatainak módosítása ID alapján | UpdateDish eljárás meghívása és a módosítani kívánt étel ID-ját megadni. | 200-as kód: Étel sikeres frissítése | 200-as kód: Étel sikeres frissítése | Pass | 2026-01-20 | Pásztor Kevin
18 | CPG-29 | Egy fizetés hozzáadása az adatbázishoz |  | 201-es kód: A fizetés sikeresen létrehozva | 400-as kód: A megadott rendelés nem létezik | Fail | 2026-01-26 | Pásztor Kevin
19 | CPG-29 | Egy fizetés hozzáadása az adatbázishoz |  | 201-es kód: A fizetés sikeresen létrehozva | 201-es kód: A fizetés sikeresen létrehozva | Pass | 2026-01-26 | Pásztor Kevin
20 | CPG-29 | Összes fizetés lekérdezése |  | 200-as kód: Összes étel sikeresen lekérdezve | 200-as kód: Összes étel sikeresen lekérdezve | Pass | 2026-01-26 | Pásztor Kevin
21 | CPG-29 | Egy fizetés törlése |  | 200-as kód: A fizetés sikeresen törölve. | 200-as kód: A fizetés sikeresen törölve. | Pass | 2026-01-26 | Pásztor Kevin
22 | CPG-29 | Egy fizetés lekérdezése egy leadott rendelés alapján |  | 200-as kód: Sikeres lekérdezés | 200-as kód: Sikeres lekérdezés | Pass | 2026-01-26 | Pásztor Kevin
23 | CPG-29 | Egy fizetés lekérdezése a fizetés ID-ja alapján |  | 200-as kód: Sikeres lekérdezés | 200-as kód: Sikeres lekérdezés | Pass | 2026-01-26 | Pásztor Kevin
24 | CPG-30 | Regisztráció során megadott jelszó követelményei | CreateUser eljárást meghívni, megadni az adatokat, viszont a jelszó megadásakor kihagyjuk a speciális karaktert | 400-as kód: A jelszónak tartalmaznia kell legalább egy speciális karaktert. | 400-as kód: A jelszónak tartalmaznia kell legalább egy speciális karaktert. | Pass | 2026-01-27 | Pásztor Kevin
25 | CPG-30 | Regisztráció során megadott jelszó követelményei |  | 400-as kód: A jelszónak tartalmaznia kell legalább egy nagybetűt. | 400-as kód: A jelszónak tartalmaznia kell legalább egy nagybetűt. | Pass | 2026-01-27 | Pásztor Kevin
26 | CPG-30 | Regisztráció során megadott jelszó követelményei |  | 201-es kód: Sikeres regisztráció | 201-es kód: Sikeres regisztráció | Pass | 2026-01-27 | Pásztor Kevin
27 | CPG-33 | Rendelési tétel sikeres létrehozása | AddOrderItem eljárás meghívása, majd hozzá tartozó adatok beírása | 201-es kód: A rendelési tétel sikeresen létrehozva. | 201-es kód: A rendelési tétel sikeresen létrehozva. | Pass | 2026-01-27 | Pásztor Kevin
28 | CPG-36 | Rendelés létrehozása | AddOrder eljárás meghívása, majd adatok beírása és a "total_price" 0 legyen | 201-es kód: A rendelés sikeresen létrehozva. | 201-es kód: A rendelés sikeresen létrehozva. | PAss | 2026-01-29 | Pásztor Kevin
29 | CPG-36 | Tétel hozzáadása egy megrendeléshez | AddOrderItem eljárás meghívása, majd hozzá tartozó adatok beírása | 201-es kód: A rendelési tétel sikeresen létrehozva. | 201-es kód: A rendelési tétel sikeresen létrehozva. | Pass | 2026-01-29 | Pásztor Kevin
30 | CPG-36 | Tétel hozzáadása egy megrendeléshez | AddOrderItem eljárás meghívása, majd hozzá tartozó adatok beírása | 201-es kód: A rendelési tétel sikeresen létrehozva. | 201-es kód: A rendelési tétel sikeresen létrehozva. | Pass | 2026-01-29 | Pásztor Kevin
31 | CPG-36 | Rendelés ellenőrzése hogy a total_price frissült-e | GetOrderById eljárás meghívása és az adott Order ID-ját megadni | 200-as kód: A rendelés értéke frissült a rendelés összegére | 200-as kód: A rendelés értéke 0 maradt | Fail | 2026-01-29 | Pásztor Kevin
32 | CPG-36 | Rendelés ellenőrzése hogy a total_price frissült-e | GetOrderById eljárás meghívása és az adott Order ID-ját megadni | 200-as kód: A rendelés értéke frissült a rendelés összegére | 200-as kód: A rendelés értéke frissült a rendelés összegére | Pass | 2026-01-29 | Pásztor Kevin
33 | CPG-36 | Fizetés hozzárendelése egy leadott rendeléshez | AddPayment eljárás meghívása, majd megadni az Order ID-ját és a fizetés típusát (method-ját) | 201-es kód: A fizetés sikeresen létrehozva | 201-es kód: A fizetés sikeresen létrehozva | Pass | 2026-01-29 | Pásztor Kevin
34 | CPG-36 | Egy rendelésben valamelyik tétel darabszámja módosítása | UpdateOrderItem eljárás meghívása, ID megadása és quantity módosítása | 200-as kód: A rendelési tétel sikeresen frissítve. | 200-as kód: A rendelési tétel sikeresen frissítve. | Pass | 2026-01-29 | Pásztor Kevin
35 | CPG-36 | Rendelés ellenőrzése hogy a total_price frissült-e újra az UpdateOrderItem után | GetOrderById eljárás meghívása és az adott Order ID-ját megadni | 200-as kód: A rendelés értéke frissült a rendelés összegére | 200-as kód: A rendelés értéke frissült a rendelés összegére | Pass | 2026-01-29 | Pásztor Kevin
36 | CPG-36 | Egy rendelésben valamelyik tétel törlése | DeleteOrderItem eljárás meghívása, majd a törölni kívánt tétel ID-ja beírása | 200-as kód: A rendelési tétel sikeresen törölve. | 200-as kód: A rendelési tétel sikeresen törölve. | Pass | 2026-01-29 | Pásztor Kevin
37 | CPG-36 | Rendelés ellenőrzése hogy a total_price frissült-e újra az DeleteOrderItem után | GetOrderById eljárás meghívása és az adott Order ID-ját megadni | 200-as kód: A rendelési tétel sikeresen frissítve. | 200-as kód: A rendelési tétel sikeresen frissítve. | Pass | 2026-01-29 | Pásztor Kevin
38 | CPG-36 | Rendelési tétel sikertelen hozzáadása | AddOrderItem eljárás meghívása és az order_id-t kihagyni | 400-as kód: Az order_id megadása kötelező. | 400-as kód: Az order_id megadása kötelező. | Pass | 2026-02-02 | Pásztor Kevin
39 | CPG-36 | Rendelési tétel sikertelen hozzáadása | AddOrderItem eljárás meghívása és az dish_id-t kihagyni | 400-as kód: Az dish_id megadása kötelező. | 400-as kód: Az dish_id megadása kötelező. | Pass | 2026-02-02 | Pásztor Kevin
40 | CPG-36 | Rendelési tétel sikertelen hozzáadása | AddOrderItem eljárás meghívása és érvénytelen order_id-t megadni (pl:9999) | 400-as kód: A megadott rendelés nem létezik. | 400-as kód: A megadott rendelés nem létezik. | Pass | 2026-02-02 | Pásztor Kevin
41 | CPG-36 | Rendelési tétel sikertelen hozzáadása | AddOrderItem eljárás meghívása és érvénytelen dish_id-t megadni (pl:9999) | 400-as kód: A megadott étel nem létezik. | 400-as kód: A megadott étel nem létezik. | Pass | 2026-02-02 | Pásztor Kevin
42 | CPG-36 | Rendelési tétel sikertelen hozzáadása | AddOrderItem eljárás meghívása és negatív quantity-t beírni | 400-as kód: A mennyiségnek pozitív számnak kell lennie. | 400-as kód: A mennyiségnek pozitív számnak kell lennie. | Pass | 2026-02-02 | Pásztor Kevin
43 | CPG-36 | Rendelési tétel sikertelen hozzáadása | AddOrderItem eljárás meghívása és 0 quantity-t beírni | 400-as kód: A mennyiségnek pozitív számnak kell lennie. | 400-as kód: A mennyiségnek pozitív számnak kell lennie. | Pass | 2026-02-02 | Pásztor Kevin
44 | CPG-36 | Rendelési tétel sikertelen frissítése | UpdateOrderItem eljárás meghívása és egy nem létező order_id-t beírni ,majd beírni a quantity-t | 404-es kód: A rendelési tétel nem található | 404-es kód: A rendelési tétel nem található | Pass | 2026-02-02 | Pásztor Kevin
45 | CPG-36 | Rendelés tétel sikertelen törlése | DeleteOrderItem eljárás meghívása és egy nem létező ID megadása | 404-es kód: A rendelési tétel nem található. | 404-es kód: A rendelési tétel nem található. | Pass | 2026-02-02 | Pásztor Kevin
46 | CPG-36 | Üres body megadása az AddOrderItems-nél | AddOrderItems eljárás meghívása, majd a body üresen hagyása | 400-as kód: A kérés törzse üres | 415-ös kód: Unsopported media type | Fail | 2026-02-02 | Pásztor Kevin
47 | CPG-36 | Üres body megadása az OrderItems-nél | AddOrderItems eljárás meghívása, majd a body üresen hagyása | 400-as kód: A kérés törzse üres |  |  | 2026-02-02 | Pásztor Kevin
48 | CPG-36 | Érvénytelen JSON formátum megadása az AddOrderItems-nél | AddOrderItems eljárás meghívása, majd érvénytelen JSON formátumot megadni | 400-as kód: Érvénytelen JSON formátum | 400-as kód: Érvénytelen JSON formátum | Pass | 2026-02-02 | Pásztor Kevin
49 | CPG-43 | Összes étterem lekérdezése | GetAllRestaurants eljárás meghívása | 200-as kód: Sikeres lekérdezés | 200-as kód: Sikeres lekérdezés | Pass | 2026-02-05 | Pásztor Kevin
50 | CPG-43 | Egy étterem lekérdezése ID alapján | GetRestaurantById eljárás meghívása, majd egy étterem ID-ját megadni | 200-as kód: Sikeres lekérdezés | 200-as kód: Sikeres lekérdezés | Pass | 2026-02-05 | Pásztor Kevin
51 | CPG-43 | Egy étterem lekérdezése olyan ID alapján ami nem létezik (pl: 9999) | GetRestaurantById eljárás meghívása, majd egy nem létező étterem ID-ját megadni | 404-es kód: Az étterem nem található | 404-es kód: Az étterem nem található | Pass | 2026-02-05 | Pásztor Kevin
52 | CPG-43 | Egy étterem lekérdezése pontos cím alapján | SearchRestaurantByAddress eljárás meghívása, majd egy pontos cím megadása (pl: 7621 Pécs, Király utca 23-25.) | 200-as kód: Sikeres lekérdezés | 200-as kód: Sikeres lekérdezés | Pass | 2026-02-05 | Pásztor Kevin
53 | CPG-43 | Új étterem sikeres létrehozása | AddRestaurant eljárás meghívása majd adatok megadása | 201-es kód: Étterem sikeresen létrehozva | 201-es kód: Étterem sikeresen létrehozva | Pass | 2026-02-05 | Pásztor Kevin
54 | CPG-43 | Új étterem sikertelen létrehozása (név megadás kihagyása) | AddRestaurant eljárás meghívása majd adatok megadása, de a "name" adatot üresen hagyni | 400-as kód: Az étterem neve megadása kötelező | 400-as kód: Az étterem neve megadása kötelező | Pass | 2026-02-05 | Pásztor Kevin
55 | CPG-43 | Meglévő étterem módosítás | UpdateRestaurant eljárás meghívása, majd a módosítandó étterem ID-ja megadása és a módosítandó adatok beírása | 200-as kód: Étterem sikeres módosítása | 200-as kód: Étterem sikeres módosítása | Pass | 2026-02-05 | Pásztor Kevin
56 | CPG-43 | Nem létező étterem törlése | DeleteRestaurant eljárás meghívása és egy nem létező étterem ID-ját megadni | 404-es kód: Az étterem nem található | 404-es kód: Az étterem nem található | Pass | 2026-02-05 | Pásztor Kevin
57 | CPG-43 | Étterem törlése | DeleteRestaurant eljárás meghívása és egy étterem ID-ját megadni | 200-as kód: Az étterem sikeresen törölve. | 200-as kód: Az étterem sikeresen törölve. | Pass | 2026-02-05 | Pásztor Kevin
58 | CPG-51 | Összes felhasználó lekérése | GetAllUsers eljárás meghívása | 200-as kód: Felhasználók sikeres lekérése | 200-as kód: Felhasználók sikeres lekérése | Pass | 2026-02-16 | Pásztor Kevin
59 | CPG-51 | Egy felhasználó lekérése ID alapján | GetUserById eljárás meghívása és a kívánt ID-t megadni | 200-as kód: Felhasználók sikeres lekérése | 200-as kód: Felhasználók sikeres lekérése | Pass | 2026-02-17 | Pásztor Kevin
60 | CPG-51 | Egy felhasználó lekérése nem létező ID alapján | GetUserById eljárás meghívása és a nem létező ID-t megadni | 404-es kód: A felhasználó nem található. | 404-es kód: A felhasználó nem található. | Pass | 2026-02-17 | Pásztor Kevin
61 | CPG-51 | Felhasználó létrehozása | CreateUser eljárás meghívása és adatok beírása | 201-es kód: User sikeresen létrehozva | 201-es kód: User sikeresen létrehozva | Pass | 2026-02-17 | Pásztor Kevin
62 | CPG-51 | Felhasználó létrehozásának próbálása foglalt email-címmel | CreateUser eljárás meghívása és adatok beírása de egy már regisztrált emailt megadni | 409-es kód: Üzenetet küldd, hogy az email-cím foglalt | 409-es kód: Üzenetet küldd, hogy az email-cím foglalt | Pass | 2026-02-17 | Pásztor Kevin
63 | CPG-51 | Bejelentkezés | Login eljárás meghívása, majd megadni az emailt és jelszót | 200-as kód: Sikeres bejelentkezés | 200-as kód: Sikeres bejelentkezés | Pass | 2026-02-17 | Pásztor Kevin
64 | CPG-51 | Bejelentkezés rossz jelszóval | Login eljárás meghívása, majd megadni az emailt és hibás jelszót | 401-es kód: Hibás jelszó | 401-es kód: Hibás jelszó | Pass | 2026-02-17 | Pásztor Kevin
65 | CPG-51 | Felhasználó adatainak módosítása | UpdateUser eljárás meghívása, felhasználó ID-ját megadni és kívánt változásokat megadni | 200: A felhasználó sikeresen frissítve. | 200: A felhasználó sikeresen frissítve. | Pass | 2026-02-17 | Pásztor Kevin
66 | CPG-51 | Nem létező felhasználó adatainak módosítása | UpdateUser eljárás meghívása, nem létező felhasználó ID-ját megadni | 404: A felhasználó nem található | 404: A felhasználó nem található | Pass | 2026-02-17 | Pásztor Kevin
67 | CPG-51 | Felhasználó törlése | DeleteUser eljárás meghívása majd kívánt ID megadása | 200: felhasználó sikeres törlése | 200: felhasználó sikeres törlése | Pass | 2026-02-17 | Pásztor Kevin
68 | CPG-51 | Nem létező felhasználó Felhasználó törlése | DeleteUser eljárás meghívása majd nem létező ID megadása | 404: felhasználó nem található | 404: felhasználó nem található | Pass | 2026-02-17 | Pásztor Kevin
69 | CPG-51 | Összes étterem lekérdezése | GetAllRestaurants eljárás meghívása | 200: Étteremek sikeres lekérdezése | 200: Étteremek sikeres lekérdezése | Pass | 2026-02-17 | Pásztor Kevin
70 | CPG-51 | Étterem létrehozása | AddRestaurant eljárás meghívása és adatok megadása | 201: Étterem sikeresen létrehozva | 201: Étterem sikeresen létrehozva | Pass | 2026-02-17 | Pásztor Kevin
71 | CPG-51 | Étterem létrehozása név megadása nélkül | AddRestaurant eljárás meghívása és adatok megadása de név kihagyása | 400: Az étterem neve kötelező. | 400: Az étterem neve kötelező. | Pass | 2026-02-17 | Pásztor Kevin
72 | CPG-51 | Étterem adatainak frissítése | UpdateRestaurant eljárás meghívása, majd a módosítandó étterem ID-ja megadása és a módosítandó adatok beírása | 200: Étterem sikeres frissítése | 200: Étterem sikeres frissítése | Pass | 2026-02-17 | Pásztor Kevin
73 | CPG-51 | nem létező Étterem adatainak frissítése | UpdateRestaurant eljárás meghívása és nem létező ID megadása | 404: Étterem nem található | 404: Étterem nem található | Pass | 2026-02-17 | Pásztor Kevin
74 | CPG-51 | Étterem törlése | DeleteRestaurant eljárás meghívása és étterem ID-ja megadása | 200:Étterem sikeres törlése | 200:Étterem sikeres törlése | Pass | 2026-02-17 | Pásztor Kevin
75 | CPG-51 | nem létező Étterem törlése | DeleteRestaurant eljárás meghívása és nem létező étterem ID-ja megadása | 404: Étterem nem található | 404: Étterem nem található | Pass | 2026-02-17 | Pásztor Kevin
76 | CPG-51 | Étterem lekérdezése cím alapján | SearchRestaurantByAddress eljárás meghívása, majd egy cím megadása (pl: 7621 Pécs, Király utca 23-25.) | 200: Sikeres lekérdezés | 200: Sikeres lekérdezés | Pass | 2026-02-17 | Pásztor Kevin
77 | CPG-51 | Étterem lekérdezése cím alapján (olyan cím ahol nincs étterem Pl:Budapest) | SearchRestaurantByAddress eljárás meghívása, majd egy hibás cím megadása (pl: Budapest) | 200: Sikeres lekérdezés (üres tömb) | 200: Sikeres lekérdezés (üres tömb) | Pass | 2026-02-17 | Pásztor Kevin
78 | CPG-51 | Egy étel lekérdezése az ID-ja alapján | GetDishByID eljárás meghívása, majd egy étel ID-t beírni (pl: dishes/GetDishById/99) | 200: Sikeres lekérdezés | 200: Sikeres lekérdezés | Pass | 2026-02-17 | Pásztor Kevin
79 | CPG-51 | Egy étel lekérdezése nem létező ID alapján | GetDishByID eljárás meghívása, majd egy étel ID-t beírni (pl: dishes/GetDishById/9999999) | 404: Az étel nem található | 404: Az étel nem található | Pass | 2026-02-17 | Pásztor Kevin
80 | CPG-51 | Összes étel lekérdezése | GetAllDishes eljárás meghívása | 200: Ételek sikeres lekérdezése | 200: Ételek sikeres lekérdezése | Pass | 2026-02-17 | Pásztor Kevin
81 | CPG-51 | Ételek lekérdezése adott étteremből | GetDishesByRestaurant eljárás meghívása és egy étterem ID-ja megadása | 200: Ételek sikeres lekérdezése | 200: Ételek sikeres lekérdezése | Pass | 2026-02-17 | Pásztor Kevin
82 | CPG-51 | Ételek lekérdezése nem létező étteremből | GetDishesByRestaurant eljárás meghívása és egy nem létező étterem ID-ja megadása | 200: Ételek sikeres lekérdezése(üres tömb) | 200: Ételek sikeres lekérdezése(üres tömb) | Pass | 2026-02-17 | Pásztor Kevin
83 | CPG-51 | Étel hozzáadása egy étteremhez | AddDish eljárás meghívása, majd az adatok beírása | 200: Az étel sikeresen létrehozva. | 200: Az étel sikeresen létrehozva. | Pass | 2026-02-17 | Pásztor Kevin
84 | CPG-51 | Étel hozzáadása egy étteremhez rossz étterem ID-val | AddDish eljárás meghívása, majd nem létező étterem ID-ját megadni | 400: A megadott étterem nem létezik. | 400: A megadott étterem nem létezik. | Pass | 2026-02-17 | Pásztor Kevin
85 | CPG-51 | Étel frissítése | UpdateDish eljárás meghívása és a módosítani kívánt étel ID-ját megadni. | 200: Az étel sikeresen frissítve. | 200: Az étel sikeresen frissítve. | Pass | 2026-02-17 | Pásztor Kevin
86 | CPG-51 | Étel frissítése nem létező ID-t megadni | UpdateDish eljárás meghívása és a nem létező ID-t megadni. | 404: Az étel nem található. | 404: Az étel nem található. | Pass | 2026-02-17 | Pásztor Kevin
87 | CPG-51 | Étel törlése | DeleteDish eljárás meghívása és az étel ID beírásával (pl: dishes/DeleteDish/5) | 200: Az étel sikeresen törölve | 200: Az étel sikeresen törölve | Pass | 2026-02-17 | Pásztor Kevin
88 | CPG-51 | Nem létező étel törlése | DeleteDish eljárás meghívása és nem létező étel ID beírásával (pl: dishes/DeleteDish/99999) | 404: Az étel nem található | 404: Az étel nem található | Pass | 2026-02-17 | Pásztor Kevin
89 | CPG-51 | Összes rendelés lekérdezése | GetAllOrders eljárás meghívása | 200: Rendelések sikeres lekérdezése | 200: Rendelések sikeres lekérdezése | Pass | 2026-02-17 | Pásztor Kevin
90 | CPG-51 | Egy rendelés lekérdezése ID alapjján | GetOrderById eljárás meghívása és az adott Order ID-ját megadni | 200: Rendelés sikeres lekérdezése | 200: Rendelés sikeres lekérdezése | Pass | 2026-02-17 | Pásztor Kevin
91 | CPG-51 | Egy rendelés lekérdezése nem létező ID alapján | GetOrderById eljárás meghívása és nem létező Order ID-t megadni | 404: A rendelés nem található | 404: A rendelés nem található | Pass | 2026-02-17 | Pásztor Kevin
92 | CPG-51 | Rendelések lekérdezése userID alapján | GetOrderByUser eljárás meghívása és egy felhasználó ID-t megadni | 200: Sikeres lekérdezés | 200: Sikeres lekérdezés | Pass | 2026-02-17 | Pásztor Kevin
93 | CPG-51 | Rendelések lekérdezése nem létező userID alapján | GetOrderByUser eljárás meghívása és egy nem létező felhasználó ID-t megadni | 200: Ételek sikeres lekérdezése(üres tömb) | 200: Ételek sikeres lekérdezése(üres tömb) | Pass | 2026-02-17 | Pásztor Kevin
94 | CPG-51 | Rendelés Leadása | AddOrder eljárás meghívása és adatok megadása | 201: Rendelés sikeresen leadva | 201: Rendelés sikeresen leadva | Pass | 2026-02-17 | Pásztor Kevin
95 | CPG-51 | Rendelés Leadása rossz felhasználó ID-val | AddOrder eljárás meghívása és rossz felhasználó ID megadása | 404: A megadott felhasználó nem létezik | 404: A megadott felhasználó nem létezik | Pass | 2026-02-17 | Pásztor Kevin
96 | CPG-51 | Rendelés frissítése | UpdateOrder eljárás meghívása és adatok beírása | 200: A rendelés sikeresen frissítve | 200: A rendelés sikeresen frissítve | Pass | 2026-02-17 | Pásztor Kevin
97 | CPG-51 | Rendelés frissítése rossz ID-val | UpdateOrder eljárás meghívása és rossz étel ID beírása | 404: A rendelés nem található | 404: A rendelés nem található | Pass | 2026-02-17 | Pásztor Kevin
98 | CPG-51 | Rendelés törlése | DeleteOrder eljárás meghívása és rendelés ID megadása | 200: Rendelés Sikeres törlése | 200: Rendelés Sikeres törlése | Pass | 2026-02-17
99 | CPG-51 | Rendelés törlése rossz ID-val | DeleteOrder eljárás meghívása és rossz rendelés ID megadása | 404: A rendelés nem található | 404: A rendelés nem található | Pass | 2026-02-17
100 | CPG-51 | Összes rendelési tétel lekérdezése | GetAllOrderItems eljárás meghívása | 200: Összes tétel sikeres lekérdezése | 200: Összes tétel sikeres lekérdezése | Pass | 2026-02-17
101 | CPG-51 | Egy rendelési tétel lekérdezése ID alapján | GetOrderItemById eljárás meghívása majd egy rendelési tétel ID megadása | 200: Sikeres lekérdezés | 200: Sikeres lekérdezés | Pass | 2026-02-17
102 | CPG-51 | Egy rendelési tétel lekérdezése rossz ID alapján | GetOrderItemById eljárás meghívása majd egy nem létező rendelési tétel ID megadása | 404: A rendelési tétel nem található | 404: A rendelési tétel nem található | Pass | 2026-02-17
103 | CPG-51 | Rendelési tételek kiírása egy rendelés ID alapján | GetOrderItemsByOrder eljárás meghívása és egy rendelés ID-t megadni | 200: Sikeres lekérdezés | 200: Sikeres lekérdezés | Pass | 2026-02-17
104 | CPG-51 | Rendelési tételek kiírása egy nem létező rendelés ID alapján | GetOrderItemsByOrder eljárás meghívása és egy nem létező rendelés ID-t megadni | 200: Sikeres lekérdezés(üres tömb) | 200: Sikeres lekérdezés(üres tömb) | Pass | 2026-02-17
105 | CPG-51 | Rendelési tétel hozzáadása egy rendeléshez | AddOrderItem meghívása és egy rendelés ID-ját megadni | 200: A rendelési tétel sikeresen frissítve | 200: A rendelési tétel sikeresen frissítve | Pass | 2026-02-17
106 | CPG-51 | Rendelési tétel hozzáadása egy rendelésheő nem létező tétel ID-val | AddOrderItem meghívása és egy nem létező rendelés ID-ját megadni | 404: A rendelési tétel nem található | 404: A rendelési tétel nem található | Pass | 2026-02-17
107 | CPG-51 | Rendelési tétel törlése | DeleteOrderItem meghívása és egy rendelési tétel ID megadása | 200: Rendelési tétel sikeres törlése | 200: Rendelési tétel sikeres törlése | Pass | 2026-02-17
108 | CPG-51 | Minden fizetés lekérdezése | GetAllPayments eljárás meghívása | 200: Minden fizetés sikeres lekérdezése | 200: Minden fizetés sikeres lekérdezése | Pass | 2026-02-17
109 | CPG-51 | Fizetés lekérdezése egy fizetés ID alapján | GetPaymentById eljárás meghívása és egy fizetés ID-ja megadása | 200: Sikeres lekérdezés | 200: Sikeres lekérdezés | Pass | 2026-02-17
110 | CPG-51 | Fizetés lekérdezése egy rendelés ID alapján | GetPaymentByOrder eljárás meghívása és egy rendelés ID megadása | 200: Sikeres lekérdezés | 200: Sikeres lekérdezés | Pass | 2026-02-17
111 | CPG-51 | Fizetés hozzárendelése egy leadott rendeléshez | AddPayment eljárás meghívása, majd megadni az Order ID-ját és a fizetés típusát | 201: Fizetés sikeresen hozzáadva | 201: Fizetés sikeresen hozzáadva | Pass | 2026-02-17
112 | CPG-51 | Fizetés hozzárendelése egy leadott rendeléshez (más összeg megadása mint a rendelésnél) | AddPayment eljárás meghívása, majd megadni az Order ID-ját és a fizetés típusát | 201: Fizetés sikeresen hozzáadva | 500: A fizetés összege nem egyezik meg a rendelés összegével | Fail | 2026-02-17
113 | CPG-51 | Fizetés frissítése | UpdatePayment eljárás meghívása és egy fizetés ID-ját megadni, majd frissíteni kívánt adatoot beírni | 200: A fizetés sikeresen frissítve | 200: A fizetés sikeresen frissítve | Pass | 2026-02-17
114 | CPG-51 | Fizetés törlése | DeletePayment eljárás meghívása és egy fizetés ID-t megadni | 200: A fizetés sikeresen törölve. | 200: A fizetés sikeresen törölve. | Pass | 2026-02-17
115 | CPG-51
116 | CPG-51
117 | CPG-51
118 | CPG-51
119 | CPG-51
120 | CPG-51
121 | CPG-51
122 | CPG-51
123 | CPG-51
124 | CPG-51
125 | CPG-51
126 | CPG-51
127 | CPG-51
128 | CPG-51
129 | CPG-51
130 | CPG-51
131 | CPG-51
132 | CPG-51
133 | CPG-51
134 | CPG-51
135 | CPG-51
136 | CPG-51
137 | CPG-51
138
139
140
141
142
143
Formulas:
Date = [Date, row above]

## Adatbázis
# USERS
ID | Task ID | TestObjektiv | TestSteps | ExpectedResult | ActualResult | Pass/Fail | Date | Done by
1 | 1 | AddUser tesztelése | AddUser('Teszt User','teszt@example.com','hash123','+3612345678','Budapest','customer') | Új user létrejön, user_id automatikusan generálva | Új user sikeresen létrejött | Pass | 2025-10-03 | Kuti Levente
2 | 2 | GetAllUsers tesztelése | GetAllUsers() | Minden user megjelenik | Korábban létrehozott user szerepel | Pass | 2025-10-04 | Kuti Levente
3 | 3 | UpdateUser tesztelése | UpdateUser(1,'Updated Name','updated@example.com','hash123','+36111223344','Debrecen','admin') | A user adatai frissültek | Adatok sikeresen frissültek | Pass | 2025-10-05 | Kuti Levente
4 | 4 | DeleteUser tesztelése | DeleteUser(1) | User törölve | Adatbázisból törölve | Pass | 2025-10-06 | Kuti Levente
5 | 5 | GetUserById tesztelése | GetUserById(2) | User adatai megjelennek | Adatok helyesen jelennek meg | Pass | 2025-10-15 | Kuti Levente
6 | 6 | CreateUser tesztelése | CreateUser('Új User','uj@example.com','ujhash','+36202223344','Szeged','customer') | Új user létrejön, user_id automatikusan generálva | Új user sikeresen létrejött | Pass | 2025-10-16 | Kuti Levente
# RESTAURANTS
ID | Task ID | TestObjektiv | TestSteps | ExpectedResult | ActualResult | Pass/Fail | Date | Done by
7 | 7 | AddRestaurant tesztelése | AddRestaurant(1,'Pizza Place','Finom pizzák','Budapest','+361234567','11:00-22:00') | Új étterem létrehozva | Étterem sikeresen létrejött | Pass | 2025-10-07 | Kuti Levente
8 | 8 | GetAllRestaurants tesztelése | GetAllRestaurants() | Minden étterem listázva | Korábban hozzáadott étterem szerepel | Pass | 2025-10-08 | Kuti Levente
9 | 9 | UpdateRestaurant tesztelése | UpdateRestaurant(1,'Updated Pizza','Új leírás','Debrecen','+361112233','12:00-23:00') | Adatok frissítve | Étterem adatai frissültek | Pass | 2025-10-09 | Kuti Levente
10 | 10 | DeleteRestaurant tesztelése | DeleteRestaurant(1) | Étterem törölve | Étterem sikeresen törölve | Pass | 2025-10-10 | Kuti Levente
# DISHES
ID | Task ID | TestObjektiv | TestSteps | ExpectedResult | ActualResult | Pass/Fail | Date | Done by
11 | 11 | AddDish tesztelése | AddDish(1,'Margherita','Paradicsom, sajt',2290,'',TRUE) | Új étel létrehozva | Étel sikeresen létrejött | Pass | 2025-11-01 | Kuti Levente
12 | 12 | GetAllDishes tesztelése | GetAllDishes() | Minden étel megjelenik | Korábban hozzáadott étel szerepel | Pass | 2025-11-02 | Kuti Levente
13 | 13 | UpdateDish tesztelése | UpdateDish(1,'Updated Pizza','Frissített leírás',2490,'',FALSE) | Adatok frissítve | Étel adatai frissültek | Pass | 2025-11-03 | Kuti Levente
14 | 14 | DeleteDish tesztelése | DeleteDish(1) | Étel törölve | Étel sikeresen törölve | Pass | 2025-11-04 | Kuti Levente
# ORDERS
ID | Task ID | TestObjektiv | TestSteps | ExpectedResult | ActualResult | Pass/Fail | Date | Done by
15 | 15 | AddOrder tesztelése | AddOrder(2,1,'pending',5000) | Új rendelés létrehozva | Rendelés sikeresen létrejött | Pass | 2025-11-05 | Kuti Levente
16 | 16 | GetAllOrders tesztelése | GetAllOrders() | Minden rendelés megjelenik | Korábbi rendelés szerepel | Pass | 2025-11-06 | Kuti Levente
17 | 17 | UpdateOrder tesztelése | UpdateOrder(1,'completed',5200) | Rendelés frissítve | Rendelés státusza frissült | Pass | 2025-11-07 | Kuti Levente
18 | 18 | DeleteOrder tesztelése | DeleteOrder(1) | Rendelés törölve | Rendelés sikeresen törölve | Pass | 2025-11-08 | Kuti Levente
# ORDER ITEMS
ID | Task ID | TestObjektiv | TestSteps | ExpectedResult | ActualResult | Pass/Fail | Date | Done by
19 | 19 | AddOrderItem tesztelése | AddOrderItem(1,1,2,2290) | Új rendelési tétel létrehozva | Tétel sikeresen létrejött | Pass | 2025-10-11 | Kuti Levente
20 | 20 | GetAllOrderItems tesztelése | GetAllOrderItems() | Minden rendelési tétel megjelenik | Korábbi tétel szerepel | Pass | 2025-10-12 | Kuti Levente
21 | 21 | UpdateOrderItem tesztelése | UpdateOrderItem(1,3,3400) | Adatok frissítve | Tétel adatai frissültek | Pass | 2025-10-13 | Kuti Levente
22 | 22 | DeleteOrderItem tesztelése | DeleteOrderItem(1) | Tétel törölve | Tétel sikeresen törölve | Pass | 2025-10-14 | Kuti Levente
# PAYMENTS
ID | Task ID | TestObjektiv | TestSteps | ExpectedResult | ActualResult | Pass/Fail | Date | Done by
23 | 23 | AddPayment tesztelése | AddPayment(1,5200,'card','pending') | Új fizetés létrehozva | Fizetés sikeresen létrejött | Pass | 2025-11-09 | Kuti Levente
24 | 24 | GetAllPayments tesztelése | GetAllPayments() | Minden fizetés megjelenik | Korábbi fizetés szerepel | Pass | 2025-11-10 | Kuti Levente
25 | 25 | UpdatePayment tesztelése | UpdatePayment(1,'paid') | Fizetés státusz frissítve | Státusz sikeresen frissült | Pass | 2025-11-11 | Kuti Levente
26 | 26 | DeletePayment tesztelése | DeletePayment(1) | Fizetés törölve | Fizetés sikeresen törölve | Pass | 2025-11-12 | Kuti Levente

## Frontend
ID | Task ID | TestObjektiv | TestSteps | ExpectedResult | ActualResult | Pass/Fail | Date | Done by:
1 | CPG-40 | Getting in the register page | 1. Open the main page 2. Click on the register button | The register button takes you to the registration page | The register button takes you to the registration page | Pass | 2026.02.20 | Kocsis Szabolcs
2 | CPG-40 | Username error | 1. Leave the username row empty 2. Click the registration button | You get an error message | You get an error message | Pass | 2026.02.20 | Kocsis Szabolcs
3 | CPG-40 | Password error | 1. Leave the password row empty 2. Click the registration button | You get an error message | You get an error message | Pass | 2026.02.20 | Kocsis Szabolcs
4 | CPG-40 | Payment button | 1. Click the payment button | You will reach the payment page | You reach the payment page | Pass | 2026.02.20 | Kocsis Szabolcs
5 | CPG-40 | Restaurants button | 1. Click the restaurants button | You will reach the restaurants page | You reach the restaurants page | Pass | 2026.02.20 | Kocsis Szabolcs
6 | CPG-40 | Navbar - Registration button | 1. Click the registration button in navbar | You will reach the registration page | You reach the registration page | Pass | 2026.02.20 | Kocsis Szabolcs
7 | CPG-40 | Navbar - Cart button | 1. Click the cart button in navbar | You will reach the cart page | You reach the cart page | Pass | 2026.02.20 | Kocsis Szabolcs
8 | CPG-40 | Main page button | 1. Click the main page button/logo | You will reach the main page | You reach the main page | Pass | 2026.02.20 | Kocsis Szabolcs
9 | CPG-40 | Each restaurants page | 1. Click the "Ugrás az oldalra" button | You will reach the restaurant homepage | You reach the restaurant homepage | Pass | 2026.02.20 | Kocsis Szabolcs
10 | CPG-40 | Login - Valid credentials | 1. Click the login button 2. Enter valid email 3. Enter valid password | You will reach the main page | You reach the main page | Pass | 2026.02.20 | Kocsis Szabolcs
11 | CPG-40 | Login - Wrong password | 1. Click the login button 2. Enter valid email 3. Enter wrong password | Login fails, error message shown | Login fails, error message shown | Pass | 2026.02.20 | Kocsis Szabolcs
12 | CPG-40 | Login - Wrong email and password | 1. Click the login button 2. Enter wrong email 3. Enter wrong password | Login fails, error message shown | Login fails, error message shown | Pass | 2026.02.20 | Kocsis Szabolcs
13 | CPG-40 | Login - Wrong email, correct password | 1. Click the login button 2. Enter wrong email 3. Enter correct password | Login fails, error message shown | Login fails, error message shown | Pass | 2026.02.20 | Kocsis Szabolcs
14 | CPG-40 | Logout functionality | 1. Click the logout button | Returns to the main page | Returns to the main page | Pass | 2026.02.20 | Kocsis Szabolcs
15 | CPG-40 | Adding items to cart | 1. Click the restaurants button 2. Place a dish in the cart | You can see the price and dish in the cart | You can see the price and dish in the cart | Pass | 2026.02.20 | Kocsis Szabolcs
16 | CPG-40 | Delete item from cart | 1. Add dish to cart 2. Click the "Törlés" button | The dish is removed from the cart | The dish is removed from the cart | Pass | 2026.02.20 | Kocsis Szabolcs
17 | CPG-40 | Increase dish quantity | 1. Add one dish to cart 2. Click the "+" button | The number and price increase | The number and price increase | Pass | 2026.02.20 | Kocsis Szabolcs
18 | CPG-40 | Decrease dish quantity | 1. Add dish and increase quantity 2. Click the "-" button | The number and price decrease | The number and price decrease | Pass | 2026.02.20 | Kocsis Szabolcs
19 | CPG-40 | Order payment complete | 1. Add dish to cart 2. Click "Tovább a fizetéshez" 3. Enter card details 4. Click "Fizetés véglegesítése" | Order saved to database, visible in profile | Order saved to database, visible in profile | Pass | 2026.02.20 | Kocsis Szabolcs
20 | CPG-40 | Address provided when paying | 1. Select item and add to cart 2. Click payment button 3. Enter address and card details 4. Proceed to payment | After payment, email received, order visible in profile | After payment, email received, order visible in profile | Pass | 2026.02.20 | Kocsis Szabolcs
21 | CPG-40 | Index page loads correctly | 1. Open index.html in browser | Page loads with hero section, navigation bar, popular restaurants section, and footer | Page loads with hero section, navigation bar, popular restaurants section, and footer | Pass | 2026.02.20 | Kocsis Szabolcs
22 | CPG-40 | Hero section CTA button | 1. Open index.html 2. Click "Éttermeink megtekintése" button | User is redirected to restaurants.html | User is redirected to restaurants.html | Pass | 2026.02.20 | Kocsis Szabolcs
23 | CPG-40 | Popular restaurants API load | 1. Open index.html 2. Wait for page load | Restaurant cards appear in "Népszerű Éttermeink" section with images | Restaurant cards appear in "Népszerű Éttermeink" section with images | Pass | 2026.02.20 | Kocsis Szabolcs
24 | CPG-40 | Navbar responsive toggle | 1. Open index.html on mobile (< 992px) 2. Click hamburger menu icon | Navigation menu expands showing all items | Navigation menu expands showing all items | Pass | 2026.02.20 | Kocsis Szabolcs
25 | CPG-40 | Footer ÁSZF link exists | 1. Scroll to footer section | ÁSZF link is visible and clickable | ÁSZF link is visible and not clickable | Fail | 2026.02.20 | Kocsis Szabolcs
26 | CPG-40 | Footer Kapcsolat link | 1. Scroll to footer 2. Click "Kapcsolat" link | User is redirected to connections.html | User is redirected to connections.html | Pass | 2026.02.20 | Kocsis Szabolcs
27 | CPG-40 | Features section display | 1. Open index.html 2. Scroll to features section | Three feature boxes: "Villámgyors kiszállítás", "Elégedett vásárlók", "Nagy választék" | Three feature boxes: "Villámgyors kiszállítás", "Elégedett vásárlók", "Nagy választék" | Pass | 2026.02.20 | Kocsis Szabolcs
28 | CPG-40 | Brand logo navigation | 1. Click on "KLSZ Faloda" logo | User navigated to index.html | User navigated to index.html | Pass | 2026.02.20 | Kocsis Szabolcs
29 | CPG-40 | Registration page loads | 1. Navigate to registration.html | Form displays with: name, username, email, phone, password, confirm password fields | Form displays with: name, username, email, phone, password, confirm password fields | Pass | 2026.02.20 | Kocsis Szabolcs
30 | CPG-40 | Empty name field validation | 1. Leave name field empty 2. Fill other fields 3. Click "Regisztrálok" | Error message: name is required | Error message: name is required | Pass | 2026.02.20 | Kocsis Szabolcs
31 | CPG-40 | Empty username validation | 1. Leave username empty 2. Fill other fields 3. Submit | Error message: username is required | Error message: username is required | Pass | 2026.02.20 | Kocsis Szabolcs
32 | CPG-40 | Invalid email format | 1. Enter invalid email (e.g., "test@") 2. Fill other fields 3. Submit | Error message: invalid email format | Error message: invalid email format | Pass | 2026.02.20 | Kocsis Szabolcs
33 | CPG-40 | Password too short | 1. Enter password < 8 characters 2. Submit form | Error: password must be at least 8 characters | Error: password must be at least 8 characters | Pass | 2026.02.20 | Kocsis Szabolcs
34 | CPG-40 | Password missing uppercase | 1. Enter password without uppercase 2. Submit form | Error: password must contain uppercase letter | Error: password must contain uppercase letter | Pass | 2026.02.20 | Kocsis Szabolcs
35 | CPG-40 | Password missing special char | 1. Enter password without special char 2. Submit form | Error: password must contain special character | Error: password must contain special character | Pass | 2026.02.20 | Kocsis Szabolcs
36 | CPG-40 | Password mismatch | 1. Enter different passwords 2. Submit form | Error: passwords do not match | Error: passwords do not match | Pass | 2026.02.20 | Kocsis Szabolcs
37 | CPG-40 | Phone number validation | 1. Enter invalid phone format 2. Submit form | Error: invalid phone number format | Error: invalid phone number format | Pass | 2026.02.20 | Kocsis Szabolcs
38 | CPG-40 | Successful registration | 1. Fill all fields with valid data 2. Passwords match requirements 3. Submit form | Success message displayed, user can login | Success message displayed, user can login | Pass | 2026.02.20 | Kocsis Szabolcs
39 | CPG-40 | Login link navigation | 1. On registration page 2. Click "Jelentkezz be!" link | User redirected to login.html | User redirected to login.html | Pass | 2026.02.20 | Kocsis Szabolcs
40 | CPG-40 | Password requirements visible | 1. View registration form | Password requirements list visible below field | Password requirements list visible below field | Pass | 2026.02.20 | Kocsis Szabolcs
41 | CPG-40 | Duplicate email error | 1. Register with existing email 2. Submit | Error: email already registered | Error: email already registered | Pass | 2026.02.20 | Kocsis Szabolcs
42 | CPG-40 | Login page loads | 1. Navigate to login.html | Login form with email and password fields | Login form with email and password fields | Pass | 2026.02.20 | Kocsis Szabolcs
43 | CPG-40 | Empty email validation | 1. Leave email empty 2. Enter password 3. Submit | Error: email is required | Error: email is required | Pass | 2026.02.20 | Kocsis Szabolcs
44 | CPG-40 | Empty password validation | 1. Enter email 2. Leave password empty 3. Submit | Error: password is required | Error: password is required | Pass | 2026.02.20 | Kocsis Szabolcs
45 | CPG-40 | Invalid credentials error | 1. Enter non-existent email 2. Enter any password 3. Submit | Error message: invalid credentials | Error message: invalid credentials | Pass | 2026.02.20 | Kocsis Szabolcs
46 | CPG-40 | Successful customer login | 1. Enter valid customer email 2. Enter correct password 3. Submit | User logged in, redirected to index or profile | User logged in, redirected to index or profile | Pass | 2026.02.20 | Kocsis Szabolcs
47 | CPG-40 | Successful admin login | 1. Enter admin email 2. Enter correct password 3. Submit | Admin logged in, access to admin-dashboard | Admin logged in, access to admin-dashboard | Pass | 2026.02.20 | Kocsis Szabolcs
48 | CPG-40 | Successful owner login | 1. Enter restaurant owner email 2. Enter correct password 3. Submit | Owner logged in, owner features available | Owner logged in, owner features available | Pass | 2026.02.20 | Kocsis Szabolcs
49 | CPG-40 | Register link navigation | 1. On login page 2. Click "Regisztrálj!" link | User redirected to registration.html | User redirected to registration.html | Pass | 2026.02.20 | Kocsis Szabolcs
50 | CPG-40 | Session persistence | 1. Login successfully 2. Refresh page | User remains logged in after refresh | User remains logged in after refresh | Pass | 2026.02.20 | Kocsis Szabolcs
51 | CPG-40 | Banned user login attempt | 1. Try to login with deleted account | Error: account is deleted message | Error: account is deleted message | Pass | 2026.02.20 | Kocsis Szabolcs
52 | CPG-40 | Remember session localStorage | 1. Login 2. Check localStorage | User data stored in localStorage | User data stored in localStorage | Pass | 2026.02.20 | Kocsis Szabolcs
53 | CPG-40 | Features section on login page | 1. Scroll down on login.html | Features section visible with 3 boxes | Features section visible with 3 boxes | Pass | 2026.02.20 | Kocsis Szabolcs
54 | CPG-40 | Restaurants page loads | 1. Navigate to restaurants.html | Page loads with restaurant list | Page loads with restaurant list | Pass | 2026.02.20 | Kocsis Szabolcs
55 | CPG-40 | Loading spinner displays | 1. Open restaurants.html | Spinner shows during API load | Spinner shows during API load | Pass | 2026.02.20 | Kocsis Szabolcs
56 | CPG-40 | All restaurants display | 1. Wait for API response | All restaurants displayed as cards | All restaurants displayed as cards | Pass | 2026.02.20 | Kocsis Szabolcs
57 | CPG-40 | Restaurant card info | 1. View any restaurant card | Card shows: image, name, description, address, phone, hours | Card shows: image, name, description, address, phone, hours | Pass | 2026.02.20 | Kocsis Szabolcs
58 | CPG-40 | Restaurant image loads | 1. View restaurant cards | Images load from API or show placeholder | Images load from API or show placeholder | Pass | 2026.02.20 | Kocsis Szabolcs
59 | CPG-40 | Navigate to restaurant page | 1. Click "Ugrás az oldalra" button | Redirected to specific restaurant page | Redirected to specific restaurant page | Pass | 2026.02.20 | Kocsis Szabolcs
60 | CPG-40 | Page title displays | 1. View page header | "Éttermeink Listája" title visible | "Éttermeink Listája" title visible | Pass | 2026.02.20 | Kocsis Szabolcs
61 | CPG-40 | Page subtitle displays | 1. View page header | Subtitle "Pécs legjobb éttermei" visible | Subtitle "Pécs legjobb éttermei" visible | Pass | 2026.02.20 | Kocsis Szabolcs
62 | CPG-40 | Restaurant card hover effect | 1. Hover over restaurant card | Card has visual hover effect | Card has visual hover effect | Pass | 2026.02.20 | Kocsis Szabolcs
63 | CPG-40 | Footer visible on restaurants | 1. Scroll to bottom | Footer with copyright and links visible | Footer with copyright and links visible | Pass | 2026.02.20 | Kocsis Szabolcs
64 | CPG-40 | Restaurant page loads | 1. Navigate to any restaurant page | Page loads with header and menu | Page loads with header and menu | Pass | 2026.02.20 | Kocsis Szabolcs
65 | CPG-40 | Menu items display | 1. View restaurant menu section | Dishes shown with name, description, price, image | Dishes shown with name, description, price, image | Pass | 2026.02.20 | Kocsis Szabolcs
66 | CPG-40 | Add single item to cart | 1. Click "Kosárba" on menu item | Item added to cart | Item added to cart | Pass | 2026.02.20 | Kocsis Szabolcs
67 | CPG-40 | Add multiple different items | 1. Add item A 2. Add item B | Both items in cart as separate entries | Both items in cart as separate entries | Pass | 2026.02.20 | Kocsis Szabolcs
68 | CPG-40 | Add same item twice | 1. Add item A 2. Add item A again | Quantity increases by 1 | Quantity increases by 2 | Pass | 2026.02.20 | Kocsis Szabolcs
69 | CPG-40 | Dish price format | 1. View menu item | Price displayed in "Ft" format | Price displayed in "Ft" format | Pass | 2026.02.20 | Kocsis Szabolcs
70 | CPG-40 | Floating cart widget | 1. Add item to cart | Floating cart summary appears | Floating cart summary appears | Pass | 2026.02.20 | Kocsis Szabolcs
71 | CPG-40 | Navigate to cart | 1. Add items 2. Click cart button | Redirected to cart.html with items | Redirected to cart.html with items | Pass | 2026.02.20 | Kocsis Szabolcs
72 | CPG-40 | Restaurant header info | 1. View restaurant page header | Restaurant name, description visible | Restaurant name, description visible | Pass | 2026.02.20 | Kocsis Szabolcs
73 | CPG-40 | Menu category display | 1. View menu section | Menu items organized clearly | Menu items organized clearly | Pass | 2026.02.20 | Kocsis Szabolcs
74 | CPG-40 | Dish image display | 1. View menu items | Dish images load properly | Dish images load properly | Pass | 2026.02.20 | Kocsis Szabolcs
75 | CPG-40 | Add to cart feedback | 1. Click "Kosárba" button | Visual feedback (animation/message) shown | Visual feedback (animation/message) shown | Pass | 2026.02.20 | Kocsis Szabolcs
76 | CPG-40 | Cart total updates | 1. Add items to cart | Floating cart shows updated total | Floating cart shows updated total | Pass | 2026.02.20 | Kocsis Szabolcs
77 | CPG-40 | Cart page loads | 1. Navigate to cart.html | Cart page loads showing contents | Cart page loads showing contents | Pass | 2026.02.20 | Kocsis Szabolcs
78 | CPG-40 | Empty cart message | 1. Open cart with no items | "A kosár üres" message displayed | "A kosár üres" message displayed | Pass | 2026.02.20 | Kocsis Szabolcs
79 | CPG-40 | Cart items display | 1. Add items 2. Open cart | Items shown with name, quantity, price | Items shown with name, quantity, price | Pass | 2026.02.20 | Kocsis Szabolcs
80 | CPG-40 | Increase quantity (+) | 1. Click "+" button on item | Quantity +1, total price updates | Quantity +1, total price updates | Pass | 2026.02.20 | Kocsis Szabolcs
81 | CPG-40 | Decrease quantity (-) | 1. Click "-" on item with qty > 1 | Quantity -1, total price updates | Quantity -1, total price updates | Pass | 2026.02.20 | Kocsis Szabolcs
82 | CPG-40 | Remove item button | 1. Click "Törlés" on item | Item removed completely | Item removed completely | Pass | 2026.02.20 | Kocsis Szabolcs
83 | CPG-40 | Total price calculation | 1. Add multiple items | Total correctly sums all items | Total correctly sums all items | Pass | 2026.02.20 | Kocsis Szabolcs
84 | CPG-40 | Restaurant name display | 1. Add items 2. View cart | Restaurant name shown above items | Restaurant name shown above items | Pass | 2026.02.20 | Kocsis Szabolcs
85 | CPG-40 | Proceed to payment | 1. Add items 2. Click "Tovább a fizetéshez" | Redirected to payment-final.html | Redirected to payment-final.html | Pass | 2026.02.20 | Kocsis Szabolcs
86 | CPG-40 | Cart persistence | 1. Add items 2. Refresh page | Cart items preserved after refresh | Cart items preserved after refresh | Pass | 2026.02.20 | Kocsis Szabolcs
87 | CPG-40 | Decrease to zero removes | 1. Item with qty 1 2. Click "-" | Item removed when qty reaches 0 | Item removed when qty reaches 1 | Pass | 2026.02.20 | Kocsis Szabolcs
88 | CPG-40 | Cart table headers | 1. View cart table | Headers: Termék, Mennyiség, Ár, Művelet | Headers: Termék, Mennyiség, Ár, Művelet | Pass | 2026.02.20 | Kocsis Szabolcs
89 | CPG-40 | Cart summary section | 1. Add items to cart | Summary section shows total | Summary section shows total | Pass | 2026.02.20 | Kocsis Szabolcs
90 | CPG-40 | Empty cart after clear | 1. Remove all items | Empty cart message appears | Empty cart message appears | Pass | 2026.02.20 | Kocsis Szabolcs
91 | CPG-40 | Payment button disabled empty | 1. View empty cart | Payment button hidden or disabled | Payment button hidden or disabled | Pass | 2026.02.20 | Kocsis Szabolcs
92 | CPG-40 | Payment page loads | 1. Navigate with cart items | Payment page loads with form | Payment page loads with form | Pass | 2026.02.20 | Kocsis Szabolcs
93 | CPG-40 | Delivery address field | 1. View payment form | Address input visible with placeholder | Address input visible with placeholder | Pass | 2026.02.20 | Kocsis Szabolcs
94 | CPG-40 | Visa default selected | 1. Load payment page | Visa is selected by default | Visa is selected by default | Pass | 2026.02.20 | Kocsis Szabolcs
95 | CPG-40 | Switch to Mastercard | 1. Click Mastercard button | Mastercard selected, card updates | Mastercard selected, card updates | Pass | 2026.02.20 | Kocsis Szabolcs
96 | CPG-40 | Switch to PayPal | 1. Click PayPal button | PayPal section displays | PayPal section displays | Pass | 2026.02.20 | Kocsis Szabolcs
97 | CPG-40 | Switch to Cash | 1. Click Készpénz button | Cash section with instructions | Cash section with instructions | Pass | 2026.02.20 | Kocsis Szabolcs
98 | CPG-40 | Card number input | 1. Enter card number | Input accepts 16 digits in groups | Input accepts 16 digits in groups | Pass | 2026.02.20 | Kocsis Szabolcs
99 | CPG-40 | Card name input | 1. Enter cardholder name | Name displays on virtual card | Name displays on virtual card | Pass | 2026.02.20 | Kocsis Szabolcs
100 | CPG-40 | Card expiry input | 1. Enter MM/YY | Expiry shows on card correctly | Expiry shows on card correctly | Pass | 2026.02.20 | Kocsis Szabolcs
101 | CPG-40 | Card CVC input | 1. Flip card 2. Enter CVC | CVC visible on card back | CVC visible on card back | Pass | 2026.02.20 | Kocsis Szabolcs
102 | CPG-40 | Flip card button | 1. Click "Kártya megfordítása" | Card flips to show back | Card flips to show back | Pass | 2026.02.20 | Kocsis Szabolcs
103 | CPG-40 | Empty address validation | 1. Leave address empty 2. Submit | Error: address required | Error: address required | Pass | 2026.02.20 | Kocsis Szabolcs
104 | CPG-40 | Empty card number validation | 1. Leave card empty 2. Submit | Error: card number required | Error: card number required | Pass | 2026.02.20 | Kocsis Szabolcs
105 | CPG-40 | Successful payment | 1. Fill all fields 2. Click "Fizetés véglegesítése" | Order created, success message, cart cleared | Order created, success message, cart cleared | Pass | 2026.02.20 | Kocsis Szabolcs
106 | CPG-40 | Order saved to database | 1. Complete payment 2. Check profile | Order appears in profile orders | Order appears in profile orders | Pass | 2026.02.20 | Kocsis Szabolcs
107 | CPG-40 | PayPal section content | 1. Select PayPal | PayPal info and redirect text shown | PayPal info and redirect text shown | Pass | 2026.02.20 | Kocsis Szabolcs
108 | CPG-40 | Cash section warning | 1. Select Cash payment | Warning about exact amount shown | Warning about exact amount shown | Pass | 2026.02.20 | Kocsis Szabolcs
109 | CPG-40 | Card visual updates | 1. Type card number | Virtual card updates in real-time | Virtual card updates in real-time | Pass | 2026.02.20 | Kocsis Szabolcs
110 | CPG-40 | Invalid card number | 1. Enter invalid card format 2. Submit | Error: invalid card number | Error: you not get error massage | Fail | 2026.02.20 | Kocsis Szabolcs
111 | CPG-40 | Invalid expiry date | 1. Enter invalid expiry 2. Submit | Error: invalid expiry date | Error: not invalid expiry date | Fail | 2026.02.20 | Kocsis Szabolcs
112 | CPG-40 | Payment method buttons | 1. View payment methods | Visa, Mastercard, PayPal, Készpénz visible | Visa, Mastercard, PayPal, Készpénz visible | Pass | 2026.02.20 | Kocsis Szabolcs
113 | CPG-40 | Cart count in navbar | 1. View payment page navbar | Cart badge shows item count | Cart badge shows item count | Pass | 2026.02.20 | Kocsis Szabolcs
114 | CPG-40 | Profile page (logged in) | 1. Login 2. Navigate to profile.html | Profile page with user info loads | Profile page with user info loads | Pass | 2026.02.20 | Kocsis Szabolcs
115 | CPG-40 | Profile redirect (not logged) | 1. Without login 2. Go to profile.html | Redirected to login.html | Redirected to login.html | Pass | 2026.02.20 | Kocsis Szabolcs
116 | CPG-40 | User name displayed | 1. View profile | User name in profile header | User name in profile header | Pass | 2026.02.20 | Kocsis Szabolcs
117 | CPG-40 | User email displayed | 1. View profile | Email in info section | Email in info section | Pass | 2026.02.20 | Kocsis Szabolcs
118 | CPG-40 | User phone displayed | 1. View profile | Phone number displayed | Phone number displayed | Pass | 2026.02.20 | Kocsis Szabolcs
119 | CPG-40 | User role displayed | 1. View profile | Role (Vásárló/Admin/Tulajdonos) shown | Role (Vásárló/Admin/Tulajdonos) shown | Pass | 2026.02.20 | Kocsis Szabolcs
120 | CPG-40 | Registration date | 1. View profile | Registration date displayed | Registration date displayed | Pass | 2026.02.20 | Kocsis Szabolcs
121 | CPG-40 | Edit profile button | 1. Click "Szerkesztés" button | Edit modal opens | Edit modal opens | Pass | 2026.02.20 | Kocsis Szabolcs
122 | CPG-40 | Edit name | 1. Open edit modal 2. Change name 3. Save | Name updated successfully | Name updated successfully | Pass | 2026.02.20 | Kocsis Szabolcs
123 | CPG-40 | Edit username | 1. Open edit modal 2. Change username 3. Save | Username updated | Username updated | Pass | 2026.02.20 | Kocsis Szabolcs
124 | CPG-40 | Edit phone | 1. Open edit modal 2. Change phone 3. Save | Phone updated | Phone updated | Pass | 2026.02.20 | Kocsis Szabolcs
125 | CPG-40 | Email not editable | 1. Open edit modal | Email field disabled/readonly | Email field disabled/readonly | Pass | 2026.02.20 | Kocsis Szabolcs
126 | CPG-40 | Orders section visible | 1. View profile right column | "Korábbi rendelések" section visible | "Korábbi rendelések" section visible | Pass | 2026.02.20 | Kocsis Szabolcs
127 | CPG-40 | Orders list loads | 1. User has orders 2. View orders section | Previous orders displayed | Previous orders displayed | Pass | 2026.02.20 | Kocsis Szabolcs
128 | CPG-40 | Order details modal | 1. Click on order item | Order details modal opens | Order details modal opens | Pass | 2026.02.20 | Kocsis Szabolcs
129 | CPG-40 | No orders message | 1. User has no orders | "Nincsenek rendelések" message | "Nincsenek rendelések" message | Pass | 2026.02.20 | Kocsis Szabolcs
130 | CPG-40 | Modal close button | 1. Open modal 2. Click close | Modal closes properly | Modal closes properly | Pass | 2026.02.20 | Kocsis Szabolcs
131 | CPG-40 | Modal cancel button | 1. Open edit modal 2. Click "Mégse" | Modal closes without saving | Modal closes without saving | Pass | 2026.02.20 | Kocsis Szabolcs
132 | CPG-40 | Profile avatar display | 1. View profile header | Avatar icon displayed | Avatar icon displayed | Pass | 2026.02.20 | Kocsis Szabolcs
133 | CPG-40 | Vertical divider visible | 1. View profile page | Divider between info and orders | Divider between info and orders | Pass | 2026.02.20 | Kocsis Szabolcs
134 | CPG-40 | Toast notifications | 1. Save profile changes | Toast notification appears | Toast notification appears | Pass | 2026.02.20 | Kocsis Szabolcs
135 | CPG-40 | Order status badge | 1. View orders list | Status badges styled per status | Status badges styled per status | Pass | 2026.02.20 | Kocsis Szabolcs
136 | CPG-40 | Order date format | 1. View order in list | Date formatted correctly | Date formatted correctly | Pass | 2026.02.20 | Kocsis Szabolcs
137 | CPG-40 | Reviews page loads | 1. Navigate to reviews.html | Reviews page with sections visible | Reviews page with sections visible | Pass | 2026.02.20 | Kocsis Szabolcs
138 | CPG-40 | Login prompt (not logged) | 1. Not logged in 2. View reviews | Login prompt displayed | Login prompt displayed | Pass | 2026.02.20 | Kocsis Szabolcs
139 | CPG-40 | Recent reviews display | 1. View reviews page | Recent reviews from all users shown | Recent reviews from all users shown | Pass | 2026.02.20 | Kocsis Szabolcs
140 | CPG-40 | Review form (logged in) | 1. Login 2. View reviews page | New review form section visible | New review form section visible | Pass | 2026.02.20 | Kocsis Szabolcs
141 | CPG-40 | Order selector dropdown | 1. Logged in 2. View review form | Dropdown shows completed orders | Dropdown shows completed orders | Pass | 2026.02.20 | Kocsis Szabolcs
142 | CPG-40 | Star rating input | 1. Select an order | 5 star buttons appear | 6 star buttons appear | Pass | 2026.02.20 | Kocsis Szabolcs
143 | CPG-40 | Star rating selection | 1. Click on 4th star | First 4 stars highlighted | First 4 stars highlighted | Pass | 2026.02.20 | Kocsis Szabolcs
144 | CPG-40 | Comment textarea | 1. View review form | Textarea with character counter | Textarea with character counter | Pass | 2026.02.20 | Kocsis Szabolcs
145 | CPG-40 | Character counter | 1. Type in comment field | Counter updates showing X/150 | Counter updates showing X/151 | Pass | 2026.02.20 | Kocsis Szabolcs
146 | CPG-40 | Submit disabled initially | 1. Load review form | Submit button disabled | Submit button disabled | Pass | 2026.02.20 | Kocsis Szabolcs
147 | CPG-40 | Submit enabled after rating | 1. Select order 2. Select rating | Submit button becomes enabled | Submit button becomes enabled | Pass | 2026.02.20 | Kocsis Szabolcs
148 | CPG-40 | Successful review submit | 1. Fill form 2. Submit | Success message, review in list | Success message, review in list | Pass | 2026.02.20 | Kocsis Szabolcs
149 | CPG-40 | My reviews section | 1. Logged in with reviews | "Az én értékeléseim" shows user reviews | "Az én értékeléseim" shows user reviews | Pass | 2026.02.20 | Kocsis Szabolcs
150 | CPG-40 | Review shows stars | 1. View any review | Star rating displayed visually | Star rating displayed visually | Pass | 2026.02.20 | Kocsis Szabolcs
151 | CPG-40 | Review shows comment | 1. View review with comment | Comment text displayed | Comment text displayed | Pass | 2026.02.20 | Kocsis Szabolcs
152 | CPG-40 | Review shows date | 1. View any review | Review date/time displayed | Review date/time displayed | Pass | 2026.02.20 | Kocsis Szabolcs
153 | CPG-40 | Review shows restaurant | 1. View review | Restaurant name displayed | Restaurant name displayed | Pass | 2026.02.20 | Kocsis Szabolcs
154 | CPG-40 | Review shows dishes | 1. View review | Ordered dishes listed | Ordered dishes listed | Pass | 2026.02.20 | Kocsis Szabolcs
155 | CPG-40 | Login link in prompt | 1. View login prompt 2. Click login link | Redirected to login.html | Redirected to login.html | Pass | 2026.02.20 | Kocsis Szabolcs
156 | CPG-40 | Rating label display | 1. Select rating | Label (Borzalmas/Rossz/stb) shown | Label (Borzalmas/Rossz/stb) shown | Pass | 2026.02.20 | Kocsis Szabolcs
157 | CPG-40 | Admin dashboard access | 1. Login as admin 2. Go to admin-dashboard.html | Dashboard loads with statistics | Dashboard loads with statistics | Pass | 2026.02.20 | Kocsis Szabolcs
158 | CPG-40 | Dashboard blocked (customer) | 1. Login as customer 2. Go to admin-dashboard | Access denied or redirected | Access denied or redirected | Pass | 2026.02.20 | Kocsis Szabolcs
159 | CPG-40 | Daily orders stat | 1. View dashboard | Today orders count displayed | Today orders count displayed | Pass | 2026.02.20 | Kocsis Szabolcs
160 | CPG-40 | Daily revenue stat | 1. View dashboard | Daily revenue in Ft displayed | Daily revenue in Ft displayed | Pass | 2026.02.20 | Kocsis Szabolcs
161 | CPG-40 | Total revenue stat | 1. View dashboard | Total revenue displayed | Total revenue displayed | Pass | 2026.02.20 | Kocsis Szabolcs
162 | CPG-40 | Total users stat | 1. View dashboard | Total user count displayed | Total user count displayed | Pass | 2026.02.20 | Kocsis Szabolcs
163 | CPG-40 | Sidebar toggle | 1. Click hamburger button | Sidebar toggles visibility | Sidebar toggles visibility | Pass | 2026.02.20 | Kocsis Szabolcs
164 | CPG-40 | Quick link - Orders | 1. Click orders link | Navigate to admin-orders.html | Navigate to admin-orders.html | Pass | 2026.02.20 | Kocsis Szabolcs
165 | CPG-40 | Quick link - Users | 1. Click users link | Navigate to admin-users.html | Navigate to admin-users.html | Pass | 2026.02.20 | Kocsis Szabolcs
166 | CPG-40 | Quick link - Payments | 1. Click payments link | Navigate to admin-payments.html | Navigate to admin-payments.html | Pass | 2026.02.20 | Kocsis Szabolcs
167 | CPG-40 | Owner sections hidden | 1. Login as admin (not owner) | Restaurant/dish sections hidden | Restaurant/dish sections hidden | Pass | 2026.02.20 | Kocsis Szabolcs
168 | CPG-40 | Owner sections visible | 1. Login as owner | Restaurant and dish sections visible | Restaurant and dish sections visible | Pass | 2026.02.20 | Kocsis Szabolcs
169 | CPG-40 | Sidebar menu items | 1. View sidebar | Dashboard, Orders, Users, Payments links | Dashboard, Orders, Users, Payments links | Pass | 2026.02.20 | Kocsis Szabolcs
170 | CPG-40 | Stat card icons | 1. View stat cards | Each card has appropriate icon | Each card has appropriate icon | Pass | 2026.02.20 | Kocsis Szabolcs
171 | CPG-40 | Quick link cards hover | 1. Hover over quick link card | Visual hover effect | Visual hover effect | Pass | 2026.02.20 | Kocsis Szabolcs
172 | CPG-40 | Admin orders page loads | 1. Navigate to admin-orders.html | Orders table loads | Orders table loads | Pass | 2026.02.20 | Kocsis Szabolcs
173 | CPG-40 | Orders table columns | 1. View table | ID, User, Restaurant, Total, Status, Date, Actions | ID, User, Restaurant, Total, Status, Date, Actions | Pass | 2026.02.20 | Kocsis Szabolcs
174 | CPG-40 | Order status display | 1. View order row | Status shown (pending/preparing/etc) | Status shown (pending/preparing/etc) | Pass | 2026.02.20 | Kocsis Szabolcs
175 | CPG-40 | Change order status | 1. Select new status 2. Save | Status updated successfully | Status updated successfully | Pass | 2026.02.20 | Kocsis Szabolcs
176 | CPG-40 | View order details | 1. Click view button | Order details displayed | Order details displayed | Pass | 2026.02.20 | Kocsis Szabolcs
177 | CPG-40 | Order ID links | 1. Click on order ID | Order details shown | Order details shown | Pass | 2026.02.20 | Kocsis Szabolcs
178 | CPG-40 | Filter orders by status | 1. Use status filter | Only matching orders shown | Only matching orders shown | Pass | 2026.02.20 | Kocsis Szabolcs
179 | CPG-40 | Orders pagination | 1. View with many orders | Pagination controls work | Pagination controls work | Pass | 2026.02.20 | Kocsis Szabolcs
180 | CPG-40 | Order total format | 1. View order totals | Prices in Ft format | Prices in Ft format | Pass | 2026.02.20 | Kocsis Szabolcs
181 | CPG-40 | Order date format | 1. View order dates | Dates formatted correctly | Dates formatted correctly | Pass | 2026.02.20 | Kocsis Szabolcs
182 | CPG-40 | Admin users page loads | 1. Navigate to admin-users.html | Users table loads | Users table loads | Pass | 2026.02.20 | Kocsis Szabolcs
183 | CPG-40 | Users table columns | 1. View table | ID, Name, Email, Phone, Role, Status, Actions | ID, Name, Email, Phone, Role, Status, Actions | Pass | 2026.02.20 | Kocsis Szabolcs
184 | CPG-40 | Edit user button | 1. Click edit on user | Edit modal opens | Edit modal opens | Pass | 2026.02.20 | Kocsis Szabolcs
185 | CPG-40 | Ban user functionality | 1. Click torles on user | User torles status changes | User torles status changes | Pass | 2026.02.20 | Kocsis Szabolcs
186 | CPG-40 | Unban user | 1. Click unban on banned user | User unbanned | ban is not available | Fail | 2026.02.20 | Kocsis Szabolcs
187 | CPG-40 | Delete user | 1. Click delete 2. Confirm | User deleted | User deleted | Pass | 2026.02.20 | Kocsis Szabolcs
188 | CPG-40 | Role badge display | 1. View users table | Role badges styled differently | Role badges styled differently | Pass | 2026.02.20 | Kocsis Szabolcs
189 | CPG-40 | Banned status indicator | 1. View banned user | Banned indicator visible | Banned indicator visible | Fail | 2026.02.20 | Kocsis Szabolcs
190 | CPG-40 | User search/filter | 1. Use search field | Users filtered by search | Users filtered by search | Pass | 2026.02.20 | Kocsis Szabolcs
191 | CPG-40 | Edit user save | 1. Edit user 2. Save changes | User updated successfully | User updated successfully | Pass | 2026.02.20 | Kocsis Szabolcs
192 | CPG-40 | Edit user cancel | 1. Edit user 2. Cancel | Modal closes, no changes | Modal closes, no changes | Pass | 2026.02.20 | Kocsis Szabolcs
193 | CPG-40 | User phone display | 1. View user row | Phone number shown | Phone number shown | Pass | 2026.02.20 | Kocsis Szabolcs
194 | CPG-40 | Payments page loads | 1. Navigate to admin-payments.html | Payments table loads | Payments table loads | Pass | 2026.02.20 | Kocsis Szabolcs
195 | CPG-40 | Payments table columns | 1. View table | ID, Order ID, Amount, Method, Status, Date | ID, Order ID, Amount, Method, Status, Date | Pass | 2026.02.20 | Kocsis Szabolcs
196 | CPG-40 | Payment method display | 1. View payment rows | Method shown (Visa/MC/PayPal/Cash) | Method shown (Visa/MC/PayPal/Cash) | Pass | 2026.02.20 | Kocsis Szabolcs
197 | CPG-40 | Payment status display | 1. View payments | Status (completed/pending/failed) | Status (completed/pending/failed) | Pass | 2026.02.20 | Kocsis Szabolcs
198 | CPG-40 | Payment amount format | 1. View amounts | Amounts in Ft format | Amounts in Ft format | Pass | 2026.02.20 | Kocsis Szabolcs
199 | CPG-40 | Payment date format | 1. View payment dates | Dates formatted correctly | Dates formatted correctly | Pass | 2026.02.20 | Kocsis Szabolcs
200 | CPG-40 | Payment order link | 1. Click order ID | Link to order details | Link to order details | Pass | 2026.02.20 | Kocsis Szabolcs
201 | CPG-40 | Payments pagination | 1. View many payments | Pagination works | Pagination works | Pass | 2026.02.20 | Kocsis Szabolcs
202 | CPG-40 | Restaurant management section | 1. Login as owner 2. View dashboard | Restaurant management visible | Restaurant management visible | Pass | 2026.02.20 | Kocsis Szabolcs
203 | CPG-40 | View owned restaurants | 1. Click "Éttermek kezelése" | Owner restaurants listed | Owner restaurants listed | Pass | 2026.02.20 | Kocsis Szabolcs
204 | CPG-40 | Edit restaurant button | 1. Click edit on restaurant | Edit modal opens | Edit modal opens | Pass | 2026.02.20 | Kocsis Szabolcs
205 | CPG-40 | Edit restaurant save | 1. Modify data 2. Save | Restaurant updated | Restaurant updated | Pass | 2026.02.20 | Kocsis Szabolcs
206 | CPG-40 | Restaurant fields editable | 1. View edit modal | Name, description, address, phone, hours editable | Name, description, address, phone, hours editable | Pass | 2026.02.20 | Kocsis Szabolcs
207 | CPG-40 | Dish management section | 1. Click "Ételek kezelése" | Dishes table loads | Dishes table loads | Pass | 2026.02.20 | Kocsis Szabolcs
208 | CPG-40 | Edit dish button | 1. Click edit on dish | Edit modal opens | Edit modal opens | Pass | 2026.02.20 | Kocsis Szabolcs
209 | CPG-40 | Edit dish price | 1. Modify price 2. Save | Dish price updated | Dish price updated | Pass | 2026.02.20 | Kocsis Szabolcs
210 | CPG-40 | Edit dish availability | 1. Toggle availability 2. Save | Availability changed | Availability changed | Pass | 2026.02.20 | Kocsis Szabolcs
211 | CPG-40 | Add new dish | 1. Click add new 2. Fill form 3. Save | New dish created | New dish created | Pass | 2026.02.20 | Kocsis Szabolcs
212 | CPG-40 | Dish image URL field | 1. View dish edit modal | Image URL field present | Image URL field present | Pass | 2026.02.20 | Kocsis Szabolcs
213 | CPG-40 | Dish restaurant select | 1. View dish edit | Restaurant dropdown present | Restaurant dropdown present | Pass | 2026.02.20 | Kocsis Szabolcs
214 | CPG-40 | Connections page loads | 1. Navigate to connections.html | Contact page loads | Contact page loads | Pass | 2026.02.20 | Kocsis Szabolcs
215 | CPG-40 | Contact info displayed | 1. View connections page | Email, phone, address visible | Email, phone, address visible | Pass | 2026.02.20 | Kocsis Szabolcs
216 | CPG-40 | Footer link works | 1. Click Kapcsolat in footer | Navigate to connections.html | Navigate to connections.html | Pass | 2026.02.20 | Kocsis Szabolcs
217 | CPG-40 | Mobile navbar toggle | 1. View on mobile 2. Click hamburger | Mobile menu opens/closes | Mobile menu opens/closes | Pass | 2026.02.20 | Kocsis Szabolcs
218 | CPG-40 | Mobile restaurant cards | 1. View restaurants on mobile | Cards stack vertically | Cards stack vertically | Pass | 2026.02.20 | Kocsis Szabolcs
219 | CPG-40 | Mobile cart page | 1. View cart on mobile | Cart reformats for mobile | Cart reformats for mobile | Pass | 2026.02.20 | Kocsis Szabolcs
220 | CPG-40 | Mobile payment form | 1. View payment on mobile | Form fits screen | Form fits screen | Pass | 2026.02.20 | Kocsis Szabolcs
221 | CPG-40 | Tablet layout | 1. View on tablet (768-992px) | Layout adjusts appropriately | Layout adjusts appropriately | Pass | 2026.02.20 | Kocsis Szabolcs
222 | CPG-40 | Mobile profile page | 1. View profile on mobile | Layout stacks vertically | Layout stacks vertically | Pass | 2026.02.20 | Kocsis Szabolcs
223 | CPG-40 | Mobile admin sidebar | 1. View admin on mobile | Sidebar collapsible | Sidebar collapsible | Pass | 2026.02.20 | Kocsis Szabolcs
224 | CPG-40 | Touch-friendly buttons | 1. Test on touch device | Buttons easily tappable | Buttons easily tappable | Pass | 2026.02.20 | Kocsis Szabolcs
225 | CPG-40 | Mobile footer | 1. View footer on mobile | Footer readable and links work | Footer readable and links work | Pass | 2026.02.20 | Kocsis Szabolcs
226 | CPG-40 | Responsive images | 1. Resize browser | Images scale appropriately | Images scale appropriately | Pass | 2026.02.20 | Kocsis Szabolcs
227 | CPG-40 | Restaurant API GET | 1. Check Network tab 2. Load restaurants | API /api/restaurants succeeds | API /api/restaurants succeeds | Pass | 2026.02.20 | Kocsis Szabolcs
228 | CPG-40 | Dishes API GET | 1. Open restaurant page | API /api/dishes returns dishes | API /api/dishes returns dishes | Pass | 2026.02.20 | Kocsis Szabolcs
229 | CPG-40 | Login API POST | 1. Submit login form | API /api/users/Login returns token | API /api/users/Login returns token | Pass | 2026.02.20 | Kocsis Szabolcs
230 | CPG-40 | Registration API POST | 1. Submit valid registration | API /api/users/CreateUser succeeds | API /api/users/CreateUser succeeds | Pass | 2026.02.20 | Kocsis Szabolcs
231 | CPG-40 | Order create API | 1. Complete checkout | API /api/orders/AddOrder creates order | API /api/orders/AddOrder creates order | Pass | 2026.02.20 | Kocsis Szabolcs
232 | CPG-40 | Reviews API GET | 1. Open reviews page | API loads recent reviews | API loads recent reviews | Pass | 2026.02.20 | Kocsis Szabolcs
233 | CPG-40 | API error handling | 1. Disable network 2. Try loading | Error message shown gracefully | Error message shown gracefully | Pass | 2026.02.20 | Kocsis Szabolcs
234 | CPG-40 | User update API PUT | 1. Edit profile 2. Save | API /api/users/UpdateUser works | API /api/users/UpdateUser works | Pass | 2026.02.20 | Kocsis Szabolcs
235 | CPG-40 | Order by user API | 1. View profile orders | API /api/orders/GetOrdersByUser works | API /api/orders/GetOrdersByUser works | Pass | 2026.02.20 | Kocsis Szabolcs
236 | CPG-40 | Review create API | 1. Submit review | API /api/reviews/AddReview works | API /api/reviews/AddReview works | Pass | 2026.02.20 | Kocsis Szabolcs
237 | CPG-40 | Payment create API | 1. Complete payment | API /api/payments/AddPayment works | API /api/payments/AddPayment works | Pass | 2026.02.20 | Kocsis Szabolcs
238 | CPG-40 | Statistics API | 1. View admin dashboard | Stats loaded from API | Stats loaded from API | Pass | 2026.02.20 | Kocsis Szabolcs
239 | CPG-40 | Cart in localStorage | 1. Add items 2. Check localStorage | Cart data saved | Cart data saved | Pass | 2026.02.20 | Kocsis Szabolcs
240 | CPG-40 | User session stored | 1. Login 2. Check localStorage | User data/token stored | User data/token stored | Pass | 2026.02.20 | Kocsis Szabolcs
241 | CPG-40 | Logout clears storage | 1. Logout 2. Check localStorage | Session data cleared | Session data cleared | Pass | 2026.02.20 | Kocsis Szabolcs
242 | CPG-40 | Cart cleared after order | 1. Complete order 2. Check cart | Cart empty after order | Cart empty after order | Pass | 2026.02.20 | Kocsis Szabolcs
243 | CPG-40 | Cart survives refresh | 1. Add items 2. Refresh 3. Check cart | Items still in cart | Items still in cart | Pass | 2026.02.20 | Kocsis Szabolcs
244 | CPG-40 | Session survives refresh | 1. Login 2. Refresh | Still logged in | Still logged in | Pass | 2026.02.20 | Kocsis Szabolcs
245 | CPG-40 | Clear all data logout | 1. Logout completely | All user data cleared | All user data cleared | Pass | 2026.02.20 | Kocsis Szabolcs
246 | CPG-40 | Restaurant ID in cart | 1. Add items 2. Check localStorage | Restaurant ID saved with cart | Restaurant ID saved with cart | Pass | 2026.02.20 | Kocsis Szabolcs
247 | CPG-40 | Protected route - profile | 1. Clear session 2. Access profile.html | Redirected to login | Redirected to login | Pass | 2026.02.20 | Kocsis Szabolcs
248 | CPG-40 | Protected route - admin | 1. Login as customer 2. Access admin pages | Access denied | Access denied | lsz | 2026.02.20 | Kocsis Szabolcs
249 | CPG-40 | XSS prevention | 1. Enter <script> in form field | Script not executed | Script not executed | Pass | 2026.02.20 | Kocsis Szabolcs
250 | CPG-40 | Password not in URL | 1. Check URL during login | Password not visible in URL | Password not visible in URL | Pass | 2026.02.20 | Kocsis Szabolcs
251 | CPG-40 | Token-based auth | 1. Check API requests | JWT token used for auth | JWT token used for auth | Pass | 2026.02.20 | Kocsis Szabolcs
252 | CPG-40 | Role-based access | 1. Customer tries admin action | Action blocked | Action blocked | Pass | 2026.02.20 | Kocsis Szabolcs
253 | CPG-40 | Session expiry | 1. Wait for session timeout | User logged out automatically | User logged out automatically | Pass | 2026.02.20 | Kocsis Szabolcs